## Sheet1
1. Fall Detection | 2. Trend Analysis | 3. Data Persistence | 4. Record Creation | 5. User Classes | 6. User Interaction | 7. Quality Assurance
1.1 Create Sensor Interaction | 2.1 Create Trend Analysis Algorithm | 3.1 Create User Data Persistence | 4.1 Create Fall Detection Records | 5.1 Add Create Profile Activity | 6.1 Add Notification Bar View | 7.1 Fall Detection Test Scripts | Spring Semester
1.2 Create Fall Detection Algorithm | 2.2 Create Short-Term Analysis | 3.2 Create Event Records Database | 4.2 Create User Response Records | 5.2 Add Settings Activity | 6.2 Add Lock Screen View | 7.2 Sister Application Test Scripts
1.3 Create ability to run in background | 2.3 Create Long-Term Analysis | 3.3 Create Settings Data Persistence | 4.3 Create Video/Audio Recording Funcitonality | 5.3 Add Edit Profile Activity | 6.3 Add Event Confirmation | 7.3 Trend Analysis Test Scripts | 2. Trend Analysis | 5. User Classes | 6. User Interaction | 7. Quality Assurance
1.4 Create ability to access contacts |  |  | 4.4 Create Location Recording Funcitonality | 5.4 Add View Records Activity | 6.4 Add Event Cancellation |  | 2.1 Create Trend Analysis Algorithm (10 days) | 5.3 Add Edit Profile Activity (2 days; 5.6) | 6.6 Post-Incident Symptom Recording (2 days; 5.5) | 7.1 Fall Detection Test Scripts (7 days; 6.6)
1.5 Create ability to send phone calls |  |  |  | 5.5 Add Update Records Activity | 6.5 Add Event Timeout |  | 2.2 Create Short-Term Analysis (10 days; 2.1) | 5.4 Add View Records Activity (3 days) | 6.7 Application Settings (3 days, 5.6) | 7.2 Sister Application Test Scripts (5 days; 7.1, 6.8)
1.6 Create ability to make phone calls |  |  |  | 5.6 Emergency Contact Account | 6.6 Post-Incident Symptom Recording |  | 2.3 Create Long-Term Analysis (7 days; 2.2) | 5.5 Add Update Records Activity (2 days; 5.4) | 6.8 UI Update (5 days; 5.3, 6.6, 6.7) | 7.3 Trend Analysis Test Scripts (3 days;7.1, 2.3)
[5 empty] | 6.7 Application Settings |  |  | 5.6 Emergency Contact Account (10 days)
6.8 UI Update
[8 empty] | Earliest: 0 - 10 Span: 10 | Earliest: 10 - 20 Span: 10 | Earliest: 20 - 27 Span: 7 |  |  | Earliest: 27 - 30 Span: 3
[8 empty] | 2.1 Create Trend Analysis Algorithm (10 days) | 2.2 Create Short-Term Analysis (10 days) | 2.3 Create Long-Term Analysis (7 days) |  |  | 7.3 Trend Analysis Test Scripts (3 days)
[8 empty] | Latest: 0 - 10 Float: 0 | Latest: 10 - 20 Float: 0 | Latest: 20 - 27 Float: 0 |  |  | Latest: 27 - 30 Float: 0
[7 empty] | Earliest: 0 | Earliest: 0 - 3 Span: 9 | Earliest: 3 - 5 Span: 8 | Earliest: 5 - 7 Span: 8 |  | Earliest: 18 - 25 Span: 7
[7 empty] | Start | 5.4 Add View Records Activity (3 days) | 5.5 Add Update Records Activity (2 days) | 6.6 Post-Incident Symptom Recording (2 days) |  | 7.1 Fall Detection Test Scripts (7 days)
[7 empty] | Latest: 0 | Latest: 6 - 9 Float: 6 | Latest: 9 - 11 Float: 6 | Latest: 11 - 13 Float: 6 |  | Latest: 18 - 25 Float: 0
[8 empty] | Earliest: 0 - 10 Span: 10 | Earliest: 10 - 12 Span: 3 |  | Earliest: 13 - 18 Span: 5 |  |  | END (CP = 30)
[8 empty] | 5.6 Emergency Contact Account (10 days) | 5.3 Add Edit Profile Activity (2 days) |  | 6.8 UI Update (5 days)
[8 empty] | Latest: 0 - 10 Float: 0 | Latest: 11 - 13 Float: 1 |  | Latest: 13 - 18 Float: 0
Earliest: 10 - 13 Span: 3
6.7 Application Settings (3 days)
[9 empty] | Latest: 10 - 13 Float: 0 |  |  |  | Earliest: 25 - 30 Span: 5
7.2 Sister Application Test Scripts (5 days)
Latest: 25 - 30 Float: 0