## Sheet1
1. Fall Detection | 2. Trend Analysis | 3. Data Persistence | 4. Record Creation | 5. User Classes | 6. User Interaction | 7. Quality Assurance
1.1 Create Sensor Interaction | 2.1 Create Trend Analysis Algorithm | 3.1 Create User Data Persistence | 4.1 Create Fall Detection Records | 5.1 Add Create Profile Activity | 6.1 Add Notification Bar View | 7.1 Fall Detection Test Scripts | Spring Semester
1.2 Create Fall Detection Algorithm | 2.2 Create Short-Term Analysis | 3.2 Create Event Records Database | 4.2 Create User Response Records | 5.2 Add Settings Activity | 6.2 Add Lock Screen View | 7.2 Sister Application Test Scripts
1.3 Create ability to run in background | 2.3 Create Long-Term Analysis | 3.3 Create Settings Data Persistence | 4.3 Create Video/Audio Recording Funcitonality | 5.3 Add Edit Profile Activity | 6.3 Add Event Confirmation | 7.3 Trend Analysis Test Scripts | 2. Trend Analysis | 5. User Classes | 6. User Interaction | 7. Quality Assurance
1.4 Create ability to access contacts |  |  | 4.4 Create Location Recording Funcitonality | 5.4 Add View Records Activity | 6.4 Add Event Cancellation |  | 2.1 Create Trend Analysis Algorithm (10 days) | 5.3 Add Edit Profile Activity (2 days; 5.6) | 6.6 Post-Incident Symptom Recording (2 days; 5.5) | 7.1 Fall Detection Test Scripts (7 days; 6.6)
1.5 Create ability to send phone calls |  |  |  | 5.5 Add Update Records Activity | 6.5 Add Event Timeout |  | 2.2 Create Short-Term Analysis (10 days; 2.1) | 5.4 Add View Records Activity (3 days) | 6.7 Application Settings (3 days, 5.6) | 7.2 Sister Application Test Scripts (5 days; 7.1, 6.8)
1.6 Create ability to make phone calls |  |  |  | 5.6 Emergency Contact Account | 6.6 Post-Incident Symptom Recording |  | 2.3 Create Long-Term Analysis (7 days; 2.2) | 5.5 Add Update Records Activity (2 days; 5.4) | 6.8 UI Update (5 days; 5.3, 6.6, 6.7) | 7.3 Trend Analysis Test Scripts (3 days;7.1, 2.3)
[5 empty] | 6.7 Application Settings |  |  | 5.6 Emergency Contact Account (10 days)
6.8 UI Update
[8 empty] | 2.1 Create Trend Analysis Algorithm (10 days) | 2.2 Create Short-Term Analysis (10 days; 2.1) | 2.3 Create Long-Term Analysis (7 days; 2.2) |  |  | 7.3 Trend Analysis Test Scripts (3 days;7.1, 2.3)
[7 empty] | Start | 5.4 Add View Records Activity (3 days) | 5.5 Add Update Records Activity (2 days; 5.4) | 6.6 Post-Incident Symptom Recording (2 days; 5.5) |  | 7.1 Fall Detection Test Scripts (7 days; 6.6)
END (CP = 30)
[8 empty] | 5.6 Emergency Contact Account (10 days) | 5.3 Add Edit Profile Activity (2 days; 5.6) |  | 6.8 UI Update (5 days; 5.3, 6.6, 6.7)
6.7 Application Settings (3 days, 5.6)
7.2 Sister Application Test Scripts (5 days; 7.1, 5.6)